OberLegacy 2002 Timeline

September	Recruit Executive Committee members

1 October	First Executive Committee meeting:

establish goals and solicitation

strategy, choose  (co)chairs  for

sub-committees

October	Recruit committee members

8 October	Begin planning OberLegacy 2002 kick-

off event

20-28 October	Fall Break : Have solicitation

assignments done!

30 October	OberLegacy web page goes live

End October	Begin publicizing OberLegacy

campaign

1 November	Mailing #1 to all seniors

early November	Campaign Kick-off!!

# November/December	Personal solicitation of seniors, faculty,

# and staff

22 December	Begin winter break

OberLegacy 2002 Timeline

3-29 January	Winter Term

February-May	Personal solicitation of seniors, faculty,

and staff

11 February	Faculty/Staff letter written

25 February	Parents’ letter written

1 March	Mailing #2 to all seniors

early March	OberLegacy Spring Fling!!

23-31 March	Spring Break

15-19 April	OberLegacy Phonathon:  call all seniors

who have not yet pledged (undergrads

register for classes!!)

19-24 May	SENIOR WEEK!  Report and thank-you

for all donors in Oberlin Review

24-27 May	Commencement/ Reunion

weekend

- Senior Picnic

- Alumni Luncheon

- JOIN THE ALUMNI ASSOCIATION!!

OberLegacy

Scholarships

# FOR students

# FROM students

Committee Handbook 2002